## Final project
Project Name | EDGES Software Testing Diploma5 Final Project1
Dilevery date | 2025-04-01
Test Design Date | 2024-07-12
Created By | Moataz Elngar
Reviewed By | Mohamed Tarek
Tester's Name | Bassant Draz
Document Content | Completion Report

## Completion Report
| Executed Test cases | Branch Coverag | Statement Coverage | Boundary value analysis coverage
App | 0 (Cunit) _ 6 (Black Box) | (4/4)*100 = 100% | (20/20)*100 =100% | ____
Backend | 0 (Cunit) _ 23 (Black Box) | (9/14)*100 = 64.3% | (166/178)*100=93.2% | ____
Course _reg | 7 (Cunit) _ 5 (Black Box) | (5/5)*100 = 100% | (19/19)*100 100% | 100%
Create Account | 12 (Cunit) _ 18 (Black Box) | (16/16)*100 = 100% | (47/47)*100 =100% | 71.4%
DB_Manager | 10 (Cunit) _ **(Black Box) | (13/18)*100 = 72.2% | (159/168)*100=94.4% | 75%
Login | 8 (Cunit) _ 5 (Black Box) | (12/14)*100 = 86% | (37/40)*100 =92.5% | ___
Overall | 91 | 82% | 94.9% | 75%
Comment | all black box test cases are making CRUD operations (related to DM_Manger) |  |  | Data base manager has all boundaries
| Failed Test cases | State transition Coverag | MC/DC
| 16 | 88.4% | it is not applicable to this software project